## General
Sprint 1 - Progress Report
Week of 02/21/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want a website that is minimal and easy to use. | - Created SRS document to capture core requirements | - Begin preliminary UI/UX design
2 | As a developer, I don't want to worry about provisioning and managing infrastructure. | - Created a hosted zone on aws route 53 for domain - Under the hosted zone, created A record that points at the s3 bucket for domain - Created a secondary A record for the www prefix that also points to the s3 bucket for domain - Incorporated github bot that posts commits on slack channel - Setup the github repository to host source code | - Look into configuring AWS Cloudfront in order to expand our app's exposure to a wider audience with low latency and high transfer speeds.
3 | As a user, I want to be able to upload a document. | - Created S3 bucket which will hold the user uploaded docs - Incorportated dropzone.js library which will handle the drag and drop feature into a text index.html page | - Investigate using a Lambda function to act as a bridge between dropzone.js and AWS S3.
4 | As a developer, I want my application to scale as necessary. | - Created s3 bucket for domain name - Setup domain nameservers to point to amazon nameservers - Deployed our test code to s3 - Created a second s3 bucket for www prefix that redirects to domain name | - Investigate how we can utilize the features of serverless computing to streamline the file management of documents within our S3 bucket.

## Risk
Risk | Mitigation
The application may run out of storage space. | Using AWS S3 ensures that our application scales effectively with respect to storage.
The application's nameservice may go down. | Offloading this responsibility to AWS Route 53 ensures maximum uptime.
We may lose track of changes to the source code made by each individual developer. | Utilizing GitHub to manage our source code ensures that all changes to code are visible to all group members.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
Amazon Route 53 | Domain name hosting
Amazon S3 | Static site hosting
Slack | Team communication

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Have to find a way to have GitHub pages link redirect to AWS S3 static site.
2 | Dropzone.js file does not have built in support to upload to S3, we have to do it ourselves.
3 | We have to make our web app page more attractive yet minimal, while being modern.
4 | Currently, there is no way to automate transferring of code from GitHub repo to S3. Amazon CodeDeploy only supports from GitHub to EC2 or ECS. We have to find a better pipeline without having to manually handle the transfer.
5 | Find a way to secure the AWS credentials when using AWS sdk to upload files to S3 via SDK Http POST