## General
Sprint 2 - Progress Report
Week of 03/21/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want to able to set a time limit for how long the document is viewable. | - Added a parameter to link generation lambda function to specify duration of link lifetime. | - Implement UI element for specifying file lifetime (i.e. dropdown menu or slider)
2 | As a user, I want to be able to retract the document I created at any moment. | - Explored options using S3/lambda functions to trigger link retraction on demand. | - Implement UI element for immediate link retraction
3 | As a user, I want to be able to generate a link to my document. | - Explored options for shortening and obscuring pre-signed URLs generated by lambda. | - Begin developing link shortening/obscuring function
4 | As a user, I want to be able to open a link to a document sent to me. | - Implemented placeholder modal alert to display generated link to user. | - Refine UI elements for displaying generated link to user.

## Risk
Risk | Mitigation
S3 bucket is unencrypted for ease of development and testing | Once upload functionality is finalized, S3 bucket encryption must be implemented
File names are present in pre-signed urls generated by lambda function | Must implement URL shortener/link obscuring function

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Expired links lead to an access denied error page, need to implement UI elements to replace this.