## General
Sprint 2 - Progress Report
Week of 03/28/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want to able to set a time limit for how long the document is viewable. | - Designed method to flag files as inactive after specified lifetime | - Implement scheduled lambda function to delete expired files
2 | As a user, I want to be able to retract the document I created at any moment. | - Designed system to flag files as retracted | - Implement scheduled lambda function to delete retracted files
3 | As a user, I want to be able to generate a link to my document. | - Implemented system to generate random string filename before upload | - Implement DynamoDB table to track filenames and lifetime/expiration
4 | As a user, I want to be able to open a link to a document sent to me. | - Redesigned link display method to use random string filenames | - Refine UI elements for displaying generated link to user.

## Risk
Risk | Mitigation
Even though links expire after the specified lifetime, files flagged as expired/retracted remain in the S3 bucket | Must create a scheduled lambda function to poll the DynamoDB table every hour and delete any files flagged as inactive

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration
AWS DynamoDB | Database Service

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | How often to check for and delete inactive files is an important issue; must find a balance that minimizes storage/compute scalability and cost.