## General
Sprint 1 - Progress Report
Week of 02/28/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want a website that is minimal and easy to use. | - Laid out basic UI/UX design foundation for our application. - Explored possibility of using Bootstrap for the development of our appllication's frontend. - Tested several Bootstrap templates to be modified to suit our applications needs. | - Continue UI/UX design. - Further modify and refine Bootstrap template
2 | As a developer, I don't want to worry about provisioning and managing infrastructure. | - Established and configured AWS API Gateway in order to test Lambda functions | - Further refine settings and configurations for the managed services used by our application. - Look into using AWS RDS to handle the database functions of our application.
3 | As a user, I want to be able to upload a document. | - Experimented with AWS Lambda for the generation of unique links for uploaded document. - Implemented first iteration of drag-and-drop functionality for our application. | - Implement a filter such that our file upload system only accepts certain file types.
4 | As a developer, I want my application to scale as necessary. | - Explored several examples applications of AWS Lambda. - Experimented with using Lambda functions for handling file uploading. | - Continue development of link generation system. - Begin developing lambda functions for retrieving files from generated links

## Risk
Risk | Mitigation
File links need to be unique enough in order ensure document security. | Our link generation system must be further developed and refined.
Users are able to upload any kind of file to our system at the moment, which poses a security risk. | We must create a filter that only allows approved document types to be uploaded.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | At the moment, users can upload files of any type to our system. This is both a storage capacity and security concern.
2 | Our link generation for documents is rudimentary at the moment. It must be able to handle a large number of links to files with a sufficient degree of uniqueness for each link.