## General
Sprint 1 - Progress Report
Week of 03/07/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want a website that is minimal and easy to use. | - Further refined front-end UI/UX design. - Added click to upload functionality alongside drag-and-drop. - Cleaned up several UI elements that were inconsistent with custom drag-and-drop solution. | - Refine UI/UX on mobile devices. - Fix app functionality on iOS devices.
2 | As a developer, I don't want to worry about provisioning and managing infrastructure. | - Implemented continuous integration pipeline using TravisCI | - Set up AWS RDS database service. - Monitor automatic builds and tests of rouce code using TravisCI
3 | As a user, I want to be able to upload a document. | - Replaced dropzone.js with custom written solution for drag-and-drop functionality - Files are now parsed and checks to make sure only certain file extensions are uploaded - Only allows pdf, doc, docx, txt, and rtf file extensions | - Integrate upload functionality to AWS - Work on the backend side of the application
4 | As a developer, I want my application to scale as necessary. | - Configured TravisCI to deploy directly to S3. - Upload limit of 15MB per file added. | - Configure AWS RDS for file upload and file retrieval.

## Risk
Risk | Mitigation
If our app is not built and tested often enough, faults or errors may present themselves in production. | Continue to monitor automatic builds and tests run by TravisCI.
Users on mobile devices may encounter faults or errors while using our app. | Run specific tests of app functionality on both iOS and Android devices.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Some UI elements are displayed incorrectly or do not function correctly on some mobile devices