## General
Sprint 1 - Progress Report
Week of 03/14/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want a website that is minimal and easy to use. | - Corrected issues with the app on iOS devices and Safari Browser | - Fix UI scaling issues on irregular window resolutions - Refine UI for displaying generated download links - Expand UI to include options for specifying file lifetimes
2 | As a developer, I don't want to worry about provisioning and managing infrastructure. | - Configured and tested API gateway endpoint for the generation of time-limited links | - Begin refining lambda function to accept user designated file lifetimes - Configure Lambda scheduling for the deletion of expired files
3 | As a user, I want to be able to upload a document. | - Expanded upload script to trigger Lambda function to generate links on file upload - Created Lambda function to generate pre-signed, time limited URL to download uploaded files | - Refine application security by experimenting with pre-signed upload URLS - Explore options for encrypting the contents of the S3 bucket containing uploaded files
4 | As a developer, I want my application to scale as necessary. | - Configured app permissions with regards to accessing certain capabilities of AWS services, namely S3 and lambda | - Begin developing solution to delete expired files to minimize content stored in S3 bucket

## Risk
Risk | Mitigation
S3 bucket is unencrypted for ease of development and testing | Once upload functionality is finalized, S3 bucket encryption must be implemented

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Some UI elements are displayed incorrectly or do not function correctly on irregular resolutions
2 | App may not function correctly on various mobile device + browser combinations