## General
Sprint 2 - Progress Report
Week of 04/04/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want to able to set a time limit for how long the document is viewable. | - set S3 bucket permissions to private and enabled encryption | - update database schema to track specified file lifetimes
2 | As a user, I want to be able to retract the document I created at any moment. | - added scheduled policy to delete expired files every 24 hours | - implement on-demand function to flag corresponding file records in database as retracted
3 | As a user, I want to be able to generate a link to my document. | - implemented 64 bit random string filenames on upload - created trigger to copy uploaded files with a 128 bit random string filename | - look into obscuring file types within generated links
4 | As a user, I want to be able to open a link to a document sent to me. | - created DynamoDB schema for tracking filenames and upload times | - look into displaying remaining file lifetime to viewer

## Risk
Risk | Mitigation
S3 bucket was previously unencrypted with put access available from any domain | Implemented policy to restrict put access to our app's domain only. Bucket was made private with encryption enabled.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration
AWS DynamoDB | Database Service

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | While filenames have been converted to random strings, the file extension is still visible in the generated URLs. Must find a way to obscure file types within these links.