## General
Week of 04/25/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want to able to set a time limit for how long the document is viewable. | - Began scripting of automated tests for file lifetime feature | - Further testing and refinement of file lifetime feature
2 | As a user, I want to be able to retract the document I created at any moment. | - Began scripting of automated tests for file retraction feature | - Further testing and refinement of file retraction feature
3 | As a user, I want to be able to generate a link to my document. | - Began scripting of automated tests for link generation system | - Further testing and refinement of link generation system
4 | As a user, I want to be able to open a link to a document sent to me. | - Began scripting of autoated tests for front-end elements | - Further testing and refinement of all front-end elements

## Risk
Risk | Mitigation
General bugs and unintended behavior | Run automated browser tests using Selenium in order to thoroughly test our application.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration
AWS DynamoDB | Database Service
Selenium | Automated Browser Testing

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Some minor scaling issues may occur on irregular resolutions/display scaling settings. Must refine bootstrap template to account for this.