## General
Week of 04/11/2018
Team 3
Karandeep Bhamra
Gerardo Rodriguez
Ryan Vitacion

## Progress
# | User Story | Progress | Goals for Next Week
1 | As a user, I want to able to set a time limit for how long the document is viewable. | - Implemented method to track file lifetime in DynamoDB using string prefixes | - Refine UI elements for specifying file lifetime using string prefixes
2 | As a user, I want to be able to retract the document I created at any moment. | - Investigated methods to implement immediate file retraction flagging using Lambda/DynamoDB | - Configure API gateway to respond to calls to the retraction function.
3 | As a user, I want to be able to generate a link to my document. | - Modified file upload string to include a prefix representing the specified file lifetime. | - Further testing and refinement of string prefix system
4 | As a user, I want to be able to open a link to a document sent to me. | - Looked into different options with respect to modal dialogs for displaying links and lifetimes to users | - Configure modal dialog in Bootstrap to retrieve file lifetime from system and display to the user

## Risk
Risk | Mitigation
File types are still present within generated links and may constitute sensitive information. | Must continue to investigate methods of obscuring these file types within the final links.

## COTS
COTS Products Used | Usage
Github | Code repository
Dropzone.js | Drag and drop file functionality
AWS Route 53 | Domain name hosting
AWS S3 | Static site hosting
Slack | Team communication
AWS Lambda | Serverless Compute
Bootstrap | Frontend Library
AWS API Gateway | API Gateway
TravisCI | Continuous Integration Pipeline
AWS SDK for JavaScript | AWS Scripting Integration
AWS DynamoDB | Database Service

## Defects, Problems, and Concerns
# | Defects, Problems, Concerns
1 | Some minor scaling issues may occur on irregular resolutions/display scaling settings. Must refine bootstrap template to account for this.